## Slide 1: TFMM Workplan & Mandate Augustin Colette & Oksana Tarasova
17th TFMM annual meeting – Utrecht (The Netherlands)

## Slide 2: Way Forward:
2016-2017 Workplan
Revised Mandate
Notes: Introducing myself

## Slide 3: Workplan 2016-2017: 1.1 « Improving tools »
# | Topic | Deliverable | Status
1.1.1.2 | Trends | Report | Publication planned 2016/05 Ongoing analysis of Eurodelta-Trends (inc. Coll HTAP)
1.1.1.3 | Eurodelta3 intercomparison | Report Peer review articles | Report published 2 papers submitted
1.1.1.4 | Twin urban/ rural sites | Scoping document in 2017 | Case studies to be presented at 2016 TFMM meeting (ES, UK, SE, CH)
1.1.1.7 | Exposure (modelled and observed) | Joint WGE/TFMM Contact group | To start in 2016
1.1.1.21 1.1.2.1 | Condensables | Workshop Report Emissions GL | A contact group has been setup Workshop TFEIP May 2016

## Slide 4: Workplan 2016-2017: 1.2 « Cooperation with parties »
# | Topic | Expected | Status
1.2.1 | Quality of EMEP observations | Workshop | Expected fall. 2016 (tbc)
1.2.2 | POP measurement campaign | measurement campaign | Confirm interest of SPs at 2016 TFMM
1.2.3 | Campaign w/ ACTRIS | measurement campaign | To be discussed at 2016 TFMM
1.2.4 | HM&POP national case studies | Report | Belarus and Poland foreseen To be discussed at 2016 TFMM

## Slide 5: Revised Mandate
Exec Body 1999 Decision
Update in 2016 :
  Workplan for specific actions
  Mandate for recurring tasks

## Slide 6: The functions of the TFMM will be to:
Plan and conduct its technical work to assist Parties in implementing the Monitoring Strategy for EMEP (2010–2019) and its review beyond this period taking into considerations best practices available and challenges met at the national level;
Interpret and assess together with the Parties the observation and modelling data, assess temporal and spatial trends and contribute to the evaluation of the impacts of the implementation of the Convention and its Protocols;
Provide a forum to the Parties to exchange views, experiences and suggestions on the quality, efficiency and sufficiency of EMEP measurements and data and their quality assurance;
Provide opportunity to the Parties to discuss performance and the need for improvements in models (EMEP models and those developed by the Parties) and in the scope of their application (such as for national assessments of air quality, assessment of transboundary fluxes and their influence on air quality at national levels, trend analyses, etc.);

## Slide 7: The functions of the TFMM will be to:
to ensure the coordinated efforts of Parties in organization and conduction of the intensive measurement periods and focused case studies, following data processing, model interpretation and results dissemination;
Provide support and facilitate involvement of Parties in Eastern Europe, the Caucasus and Central Asia for example with respect to setting up monitoring stations and national programs, case studies, use of modelling data and promoting the tools developed under EMEP during workshops and other dedicated meetings
collaborate with CCC, MSC-W, MSC-E, TF-EIP, TF-HTAP, TF-IAM, and Working Group on Effects to evaluate the gaps between emission inventories and observed concentrations, improve emission inventories used for modelling, improve the modelling tools to serve the Parties and to extend the use of TFMM data for effects assessment, ensure the consistency between the regional and hemispheric scale analyses;
Strengthen linkages with the European Union scientific programmes like Copernicus with a focus on development of common tools and regional assessments; develop joint activities with European (JRC, EEA), regional (Arctic Council) and global partners (WMO) to ensure synergies between regional and global scales, strengthening national activities,
Carry out other tasks assign to it by the EMEP Steering Body and the Executive Body.