# Status of Part Two of the EMEP Assessment Report

Out of all 49 Parties, 27 take active part in the work on the EMEP Assessment Report.

Situation has not changed, in this respect from the Workshop in Vienna in October 2002.  However, several Parties have neither completed measurement data checking process, nor have sent any draft of the national assessment.

Concerning measurement data checking, 19 Parties (70% of active Parties) have already completed, 3 Parties have partly completed and 3 have still not completed measurement data checking process. From those, who have not completed most are well advanced in this task and should finish it soon.  In this respect, a progress can be noted from the last Assessment Workshop in Vienna.

All Parties were expected to prepare elaborated drafts of their national assessments before the TFMM4 Meeting in Valencia. Before the end of the Valencia Meeting, six parties submitted elaborated drafts, seven parties submitted first drafts and 3 Parties submitted abstract of their national assessments. In addition, four Parties promised to submit their elaborated abstracts by the end of April.

National contributions for the EMEP Assessment Report are in principle limited to 10 pages. In many countries, much larger, earlier written assessment national reports already exist and they are of interest to the EMEP Assessment Task. The links to such large reports are available on the web, at present for four Parties: Czech Republic, Denmark, Latvia and Lithuania. More Parties will send us links to their existing large national reports by the end of April.

During the poster session, 13 Parties presented their work on the national contribution to the EMEP Assessment Report. All posters presented very useful and interesting information and were intensely discussed during the session. The following countries presented their national assessments during the poster session: Belarus, Denmark, France, Germany, Italy, Latvia, Lithuania, Macedonia, Norway, Poland, Spain, Sweden, Switzerland.

In general, a good progress in work on the Part Two of the EMEP Assessment Report in the period between Workshop in Vienna and TFMM Meeting in Valencia.